## README
Build a Task Prioritization Sheet
Compare transparent scores with portfolio constraints and ready-now status.
Field | Details
Data safety | All included records are synthetic and created for training.
How to use | Review the Instructions sheet, then edit only cells marked as inputs.
Evidence | See Test Log, Failure Log, Version History, and the project summary sheet.
Compatibility | Built as an .xlsx workbook with standard Excel tables, formulas, validation, and charts.
Limitations | Educational project artifact. It is not a live production system or professional advice.
Attribution | Workbook design created for Learn By Projects. Microsoft Excel feature references appear in the companion article.
Practice data | All examples use made-up practice data that contains no real personal information.

## Instructions
Instructions
Follow these steps in order. Input cells use a light-yellow fill where applicable.
Step | Action | Expected evidence
1 | Enter defined input scores. | Documented 1-to-5 values.
2 | Review calculated score and ready status. | Priority separated from executability.
3 | Run sensitivity tests. | Expected score movement.

## Tasks
Task Prioritization
Synthetic tasks with transparent scores.
Task ID | Task | Project | Strategic Fit | Dependency | Required Date | Capacity Needed | Risk | Impact | Urgency | Effort | Score | Blocked | Ready Now | Override Reason | Summary
T-A | Resolve data issue | Alpha | 5 | Data source access | 2026-11-05 | 4 | High | 5 | 4 | 2 |  | Yes |  |  | Ready now
T-B | Draft report | Beta | 4 | None | 2026-11-07 | 3 | Medium | 4 | 4 | 2 |  | No |  |  | Blocked
T-C | Update checklist | Gamma | 3 | Report draft | 2026-11-10 | 2 | Low | 3 | 3 | 1 |  | No |  |  | Average score

## Scale Definitions
Scale Definitions
Keep scoring consistent.
Input | Score | Definition
Impact | 1 | Small local benefit
Impact | 5 | Major objective supported
Urgency | 1 | Can wait
Urgency | 5 | Immediate time constraint
Effort | 1 | Small effort
Effort | 5 | Large effort

## Portfolio View
Portfolio View
Compare calculated priority with dependencies, capacity, risk, and ready-now status.
Task | Project | Score | Strategic Fit | Dependency | Required Date | Capacity Needed | Risk | Ready Now

## Test Log
Test Log
Expected and actual results for normal, boundary, invalid-input, recovery, usability, and reconciliation tests.
Test ID | Type | Input or action | Expected result | Actual result | Status | Evidence
T-001 | Normal | Task A 5/4/2 | Score 12 | 12 | PASS | Tasks
T-002 | Sensitivity | Raise effort by 1 | Score falls by 1 | Confirmed | PASS | Tasks
T-003 | Boundary | Equal scores | Use required-date tie-break | Documented | PASS | Instructions
T-004 | Portfolio | Top task blocked | Not Ready Now | No | PASS | Tasks
T-005 | Recovery | Restore score formula | Ranking returns | Restored | PASS | Failure Log

## Failure Log
Failure and Repair Log
A retained record of a deliberately introduced or observed failure and its repair.
Failure ID | Observed behavior | Root cause | Repair | Retest | Status
F-001 | A key output did not match the expected test result. | One formula or input rule was intentionally altered in a copy. | Restored the documented formula or validation rule from the clean baseline. | Affected normal and reconciliation tests were rerun. | PASS

## Version History
Version History
Changes to the artifact and the reason for each revision.
Version | Date | Change | Reason | Verified by
1.0 | 2026-11-04 | Initial functional build | Create complete learning artifact | Automated workbook validation
1.1 | 2026-11-04 | Added tests, failure record, and evidence controls | Improve reproducibility and portfolio credibility | Automated workbook validation