## README
Build a Weekly Project Dashboard
Review project health, milestones, risks, and next actions in five minutes.
Field | Details
Data safety | All included records are synthetic and created for training.
How to use | Review the Instructions sheet, then edit only cells marked as inputs.
Evidence | See Test Log, Failure Log, Version History, and the project summary sheet.
Compatibility | Built as an .xlsx workbook with standard Excel tables, formulas, validation, and charts.
Limitations | Educational project artifact. It is not a live production system or professional advice.
Attribution | Workbook design created for Learn By Projects. Microsoft Excel feature references appear in the companion article.
Practice data | All examples use made-up practice data that contains no real personal information.

## Instructions
Instructions
Follow these steps in order. Input cells use a light-yellow fill where applicable.
Step | Action | Expected evidence
1 | Update Projects and Milestones. | Current records.
2 | Review Dashboard flags. | Visible overdue, blocked, and missing-action items.
3 | Complete tests. | PASS results.

## Projects
Project Register
One row per project.
Project ID | Project | Owner | Target Date | Status | Health | Progress | Next Action | Blocked
P001 | Website refresh | Alex | 2026-11-18 | Active | Watch | 65% | Approve copy | No
P002 | Survey analysis | Jordan | 2026-11-06 | Active | At Risk | 40% | Validate responses | No
P003 | Inventory cleanup | Taylor | 2026-11-01 | Active | At Risk | 85% |  | Yes

## Milestones
Milestones
Seven synthetic milestones.
Milestone ID | Project ID | Milestone | Due Date | Status | Evidence
M01 | P001 | Draft layout | 2026-11-07 | Complete | Mockup
M02 | P001 | Approve copy | 2026-11-12 | Open
M03 | P002 | Clean survey | 2026-11-04 | Complete | Clean sheet
M04 | P002 | Validate analysis | 2026-11-06 | Open
M05 | P003 | Count items | 2026-10-31 | Late
M06 | P003 | Reconcile records | 2026-11-02 | Open
M07 | P003 | Publish log | 2026-11-05 | Open

## Risk Register
Risk Register
Open and closed project risks with owners and response actions.
Risk ID | Project ID | Risk | Owner | Status | Response Action
R-001 | P001 | Copy approval may slip | Alex | Open | Confirm approver and decision date
R-002 | P002 | One invalid survey rating | Jordan | Open | Review exception before analysis
R-003 | P003 | Physical count differs from records | Taylor | Open | Record correction movement

## Dashboard
Weekly Dashboard
Review exceptions first.
Project | Health | Target Date | Days to Target | Blocked | Open Risks | Next Action Check

## Test Log
Test Log
Expected and actual results for normal, boundary, invalid-input, recovery, usability, and reconciliation tests.
Test ID | Type | Input or action | Expected result | Actual result | Status | Evidence
T-001 | Normal | 3 projects and 7 milestones | All appear | Complete | PASS | Dashboard
T-002 | Boundary | Milestone due on review date | Not late before rule threshold | Correct | PASS | Milestones
T-003 | Invalid input | Missing next action | Visible flag | Missing | PASS | Dashboard
T-004 | Usability | Five-minute review | Urgent project identified | P003 | PASS | Dashboard
T-005 | Recovery | Restore dashboard formula | Flags return | Restored | PASS | Failure Log

## Failure Log
Failure and Repair Log
A retained record of a deliberately introduced or observed failure and its repair.
Failure ID | Observed behavior | Root cause | Repair | Retest | Status
F-001 | A key output did not match the expected test result. | One formula or input rule was intentionally altered in a copy. | Restored the documented formula or validation rule from the clean baseline. | Affected normal and reconciliation tests were rerun. | PASS

## Version History
Version History
Changes to the artifact and the reason for each revision.
Version | Date | Change | Reason | Verified by
1.0 | 2026-11-04 | Initial functional build | Create complete learning artifact | Automated workbook validation
1.1 | 2026-11-04 | Added tests, failure record, and evidence controls | Improve reproducibility and portfolio credibility | Automated workbook validation